## GENERALNE NAPOMENE
1 | Za A3, A4, A7 nije ništa još predano.
2 | Za A1, A2, A6 smo već predali ASB koliko znam? Samo je ostalo predati editabilne fajlove? U tom slučaju bi bilo dobro sve editabilne dwg-ove preglednih nacrta iz mog/AA radnog prebaciti u Izlaznu -> As built da budu zajedno s pdf-ovima. Također bi bilo dobro baciti oko na dwg/docx ostalih stvari koje predajemo, a koje su već u Izlaznoj, jer mislim da za njih nismo pripremali da budu editabilni, odnosno nismo ih "čistili"
3 | Za A1, A2, A6 su editabilni eplani također u mom/AA radnom (ti folderi bi trebali biti isti), samo je pitanje hoćemo ih ubacivati da stoje u Izlaznoj
4 | Komentirali smo da se popis doc za A6 i A7 razlikuje u nečemu, tipa kontrolna topologija, tako da na to treba baciti oko
5 | A3, A4 zadnji eplani, ujedno i editabilni, su u Tehničkoj
6 | A7 editabilni eplani su na čekanju dok Fran ne updatea prijevode
7 | Za editabilne fajlove A126 kojima se ne poklapa datum s pdf-om je razlog što se nije mijenjao sadržaj, samo su pripremljene clean verzije fajlova za slanje
8
9
10

## GoW1
[5 empty] | ` | [17 empty] | Document Review Stage 1 |  |  |  |  | Document Review Stage 2 |  |  |  |  | Document Review Stage 3
|  |  |  | GOW 3 | [18 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Numbering acc to Tehnical specification | Number Duplication colored red | Design | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Document Title IN FOLDER | Document Title | Document title in folder (MNE) | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 1.2./1.2.3 |  | PERU-01-11-111-11-001 |  |  | A | PER | E | 2 | U1 | FLD | 001 | 00 | VHHR |  | PER-E-2-U1-FLD-001-00-VHHR | Unit 1 HyCon governor series 400 block diagram | HyCon governor series 400 block diagram |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 1.2./1.2.3 | FŠ | PERU-01-11-111-12-001 |  |  | A | PER | E | 2 | U1 | SCH | 001 | 00 | VHHR |  | PER-E-2-U1-SCH-001-00-VHHR | Unit 1 turbine governor topology | Turbine governor topology | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 1.2./1.2.2. |  | PERU-01-11-111-14-003 |  |  | A | PER | E | 2 | U1 | ASB | 001 | 00 | VHHR |  | PER-E-2-U1-ASB-001-00-VHHR | Unit 1 turbine governor cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 1.2./1.2.2. |  | PERU-01-11-111-23-002 |  |  | A | PER | E | 2 | U1 | LST | 001 | 00 | VHHR |  | PER-E-2-U1-LST-001-00-VHHR | Unit 1 turbine governor equipment specification and quantities | Equipment specification and quantities - electrical part |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 1.2./1.2.2. |  | PERU-01-11-111-31-001 |  |  | A | PER | E | 2 | U1 | SCH | 002 | 00 | VHHR |  | PER-E-2-U1-SCH-002-00-VHHR | Unit 1 turbine governor circuit diagram | Circuit diagrams |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 1.2./1.2.2. |  | PERU-01-11-111-33-001 |  |  | A | PER | E | 2 | U1 | ROU | 001 | 00 | VHHR |  | PER-E-2-U1-ROU-001-00-VHHR | Unit 1 turbine governor cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 1.1. |  | PERU-01-11-111-61-002 |  |  | A | PER | E | 2 | U1 | FAT | 001 | 00 | VHHR |  | PER-E-2-U1-FAT-001-00-VHHR | Unit 2 turbine governor FAT report | FAT-Factory Acceptance Test program - electrical part |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 1.1. |  | PERU-01-11-111-52-001 |  |  | A | PER | E | 2 | U1 | CMM | 001 | 00 | VHHR |  | PER-E-2-U1-CMM-001-00-VHHR | Unit 2 turbine governor SAT report(_signed) | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 1.1. |  | PERU-01-11-111-70-002 |  |  | A | PER | E | 2 | U1 | MAN | 002 | 00 | VHHR |  | PER-E-2-U1-MAN-002-00-VHHR |  | Operation and maintenance manual - electrical part |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-12-20; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
III | II | 1.1. |  | PERU-01-11-111-70-003 |  |  | A | PER | E | 2 | U1 | MAN | 001 | 00 | VHHR |  | PER-E-2-U1-MAN-001-00-VHHR |  | HMI operating manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-09; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti | spremno sve, pregledati
I | III | 1.2./1.2.3 |  | PERU-01-11-111-34-002 |  |  | A | PER | E | 2 | U1 | SOF | 100 | 00 | VHHR |  | PER-E-2-U1-SOF-100-00-VHHR | Unit 1 turbine governor signal list | Turbine governor signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list | spremno sve, pregledati
I | III | 1.2./1.2.3 | FŠ | PERU-01-11-111-34-003 |  |  | A | PER | E | 2 | U1 | SOF | 101 | 00 | VHHR |  | PER-E-2-U1-SOF-101-00-VHHR | Unit 1 transfer functions and modelling | Transfer functions and modelling | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO |  | Izlazna dokumentacija -> As Built, fale editabilni fajlovi
I | III | 1.5./1.5.2. | FŠ | PERU-01-11-170-31-001 |  |  | A | PER | E | 8 | U1 | SCH | 001 | 00 | VHHR |  | PER-E-8-U1-SCH-001-00-VHHR | Unit 1 process control circuit diagram | Circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 1.5./1.5.2. |  | PERU-01-11-170-14-002 |  |  | A | PER | E | 8 | U1 | ASB | 001 | 00 | VHHR |  | PER-E-8-U1-ASB-001-00-VHHR | Unit 1 process control cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 1.5./1.5.2. | TT | PERU-01-11-170-23-001 |  |  | A | PER | E | 8 | U1 | LST | 001 | 00 | VHHR |  | PER-E-8-U1-LST-001-00-VHHR | Unit 1 process control equipment specification and quantities | Equipment specification and quantities |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 1.5./1.5.2. | TT | PERU-01-11-170-33-001 |  |  | A | PER | E | 8 | U1 | ROU | 001 | 00 | VHHR |  | PER-E-8-U1-ROU-001-00-VHHR | Unit 2 process control cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 1.4. |  | PERU-01-11-170-61-001 |  |  | A | PER | E | 8 | U1 | FAT | 001 | 00 | VHHR |  | PER-E-8-U1-FAT-001-00-VHHR |  | FAT-Factory Acceptance Test program |  |  | nema u ICS-u, ali za ovo nismo ni radili FAT?
I | III | 1.5./1.5.3. |  | PERU-01-11-170-34-001 |  |  | A | PER | E | 8 | U1 | SOF | 100 | 00 | VHHR |  | PER-E-8-U1-SOF-100-00-VHHR | Unit 1 process control signal list | Unit process control signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 1.5./1.5.3. |  | PERU-01-11-170-34-002 |  |  | A | PER | E | 8 | U1 | SCH | 002 | 00 | VHHR |  | PER-E-8-U1-SCH-002-00-VHHR | Overview of logical connections | Overview of logical connections |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
II | II | 1.4. |  | PERU-01-11-170-52-001 |  |  | A | PER | E | 8 | U1 | CMM | 001 | 00 | VHHR |  | PER-E-8-U1-CMM-001-00-VHHR | Unit 2 process control SAT report(_signed) | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 1.1. |  | PERU-01-11-170-70 -001 |  |  | A | PER | E | 8 | U1 | MAN | 001 | 00 | VHHR |  | PER-E-8-U1-MAN-001-00-VHHR |  | Operation and maintenance manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-03-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 1.2./1.2.1. |  | PERU-01-11-111-07-002 |  |  | A | PER | E | 2 | U1 | TSP | 001 | 00 | VHHR |  | PER-E-2-U1-TSP-001-00-VHHR | Unit 1 turbine governor technical desciption | Unit 1 turbine governor technical desciption |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 1.5./1.5.1. |  | PERU-01-11-170-07-001 |  |  | A | PER | E | 8 | U1 | TSP | 001 | 00 | VHHR |  | PER-E-8-U1-TSP-001-00-VHHR | Unit 1 technical description of process control | Unit 1 technical description of process control |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
nije spremno
djelomično spremno
|  |  | FŠ | spremno za slanje | [15 empty] | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO
|  |  | FŠ | samo en/samo mne verzija spremna za slanje | [15 empty] | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO
predano u ICS-u
postoji u DD, na čekanju do daljnjeg
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO

## GoW2
[5 empty] | ` | [17 empty] | Document Review Stage 1 |  |  |  |  | Document Review Stage 2 |  |  |  |  | Document Review Stage 3
|  |  |  | GOW 3 | [18 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Numbering acc to Tehnical specification | Number Duplication colored red | Design | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Document Title IN FOLDER | Document Title | Document title in folder (MNE) | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 2.2./2.2.3 |  | PERU-01-12-111-11-001 |  |  | A | PER | E | 2 | U2 | FLD | 001 | 00 | VHHR |  | PER-E-2-U2-FLD-001-00-VHHR | Unit 2 HyCon governor series 400 block diagram | HyCon governor series 400 block diagram |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 2.2./2.2.3 | FŠ | PERU-01-12-111-12-001 |  |  | A | PER | E | 2 | U2 | SCH | 001 | 00 | VHHR |  | PER-E-2-U2-SCH-001-00-VHHR | Unit 2 turbine governor topology | Turbine governor topology | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 2.2./2.2.2. |  | PERU-01-12-111-14-003 |  |  | A | PER | E | 2 | U2 | ASB | 001 | 00 | VHHR |  | PER-E-2-U2-ASB-001-00-VHHR | Unit 2 turbine governor cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 2.2./2.2.2. |  | PERU-01-12-111-23-002 |  |  | A | PER | E | 2 | U2 | LST | 001 | 00 | VHHR |  | PER-E-2-U2-LST-001-00-VHHR | Unit 2 turbine governor equipment specification and quantities | Equipment specification and quantities - electrical part |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 2.2./2.2.2. |  | PERU-01-12-111-31-001 |  |  | A | PER | E | 2 | U2 | SCH | 002 | 00 | VHHR |  | PER-E-2-U2-SCH-002-00-VHHR | Unit 2 turbine governor circuit diagram | Circuit diagrams |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 2.2./2.2.2. |  | PERU-01-12-111-33-001 |  |  | A | PER | E | 2 | U2 | ROU | 001 | 00 | VHHR |  | PER-E-2-U2-ROU-001-00-VHHR | Unit 2 turbine governor cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 2.1. |  | PERU-01-12-111-61-002 |  |  | A | PER | E | 2 | U2 | FAT | 001 | 00 | VHHR |  | PER-E-2-U2-FAT-001-00-VHHR | Unit 2 turbine governor FAT report | FAT-Factory Acceptance Test program - electrical part |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 2.1. |  | PERU-01-12-111-52-001 |  |  | A | PER | E | 2 | U2 | CMM | 001 | 00 | VHHR |  | PER-E-2-U2-CMM-001-00-VHHR | Unit 2 turbine governor SAT report(_signed) | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 2.1. |  | PERU-01-12-111-70-002 |  |  | A | PER | E | 2 | U2 | MAN | 002 | 00 | VHHR |  | PER-E-2-U2-MAN-002-00-VHHR |  | Operation and maintenance manual - electrical part |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-12-20; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
III | II | 2.1. |  | PERU-01-12-111-70-003 |  |  | A | PER | E | 2 | U2 | MAN | 001 | 00 | VHHR |  | PER-E-2-U2-MAN-001-00-VHHR |  | HMI operating manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-09; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti | spremno sve, pregledati
I | III | 2.2./2.2.3 |  | PERU-01-12-111-34-002 |  |  | A | PER | E | 2 | U2 | SOF | 100 | 00 | VHHR |  | PER-E-2-U2-SOF-100-00-VHHR | Unit 2 turbine governor signal list | Turbine governor signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list | spremno sve, pregledati
I | III | 2.2./2.2.3 | FŠ | PERU-01-12-111-34-003 |  |  | A | PER | E | 2 | U2 | SOF | 101 | 00 | VHHR |  | PER-E-2-U2-SOF-101-00-VHHR | Unit 2 transfer functions and modelling | Transfer functions and modelling | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO |  | Izlazna dokumentacija -> As Built, fale editabilni fajlovi
I | III | 2.5./2.5.2. | FŠ | PERU-01-12-170-31-001 |  |  | A | PER | E | 8 | U2 | SCH | 001 | 00 | VHHR |  | PER-E-8-U2-SCH-001-00-VHHR | Unit 2 process control circuit diagram | Circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 2.5./2.5.2. |  | PERU-01-12-170-14-002 |  |  | A | PER | E | 8 | U2 | ASB | 001 | 00 | VHHR |  | PER-E-8-U2-ASB-001-00-VHHR | Unit 2 process control cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 2.5./2.5.2. | TT | PERU-01-12-170-23-001 |  |  | A | PER | E | 8 | U2 | LST | 001 | 00 | VHHR |  | PER-E-8-U2-LST-001-00-VHHR | Unit 2 process control equipment specification and quantities | Equipment specification and quantities |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 2.5./2.5.2. | TT | PERU-01-12-170-33-001 |  |  | A | PER | E | 8 | U2 | ROU | 001 | 00 | VHHR |  | PER-E-8-U2-ROU-001-00-VHHR | Unit 2 process control cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 2.4. |  | PERU-01-12-170-61-001 |  |  | A | PER | E | 8 | U2 | FAT | 001 | 00 | VHHR |  | PER-E-8-U2-FAT-001-00-VHHR |  | FAT-Factory Acceptance Test program |  |  | nema u ICS-u, ali za ovo nismo ni radili FAT?
I | III | 2.5./2.5.3. |  | PERU-01-12-170-34-001 |  |  | A | PER | E | 8 | U2 | SOF | 100 | 00 | VHHR |  | PER-E-8-U2-SOF-100-00-VHHR | Unit 2 process control signal list | Unit process control signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 2.5./2.5.3. |  | PERU-01-12-170-34-002 |  |  | A | PER | E | 8 | U2 | SCH | 002 | 00 | VHHR |  | PER-E-8-U2-SCH-002-00-VHHR | Unit 2 overview of logical connections | Overview of logical connections |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
II | II | 2.4. |  | PERU-01-12-170-52-001 |  |  | A | PER | E | 8 | U2 | CMM | 001 | 00 | VHHR |  | PER-E-8-U2-CMM-001-00-VHHR | Unit 2 process control SAT report(_signed) | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 2.1. |  | PERU-01-12-170-70 -001 |  |  | A | PER | E | 8 | U2 | MAN | 001 | 00 | VHHR |  | PER-E-8-U2-MAN-001-00-VHHR |  | Operation and maintenance manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-03-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 2.2./2.2.1. |  | PERU-01-12-111-07-002 |  |  | A | PER | E | 2 | U2 | TSP | 001 | 00 | VHHR |  | PER-E-2-U2-TSP-001-00-VHHR | Unit 2 turbine governor technical desciption | Unit 2 turbine governor technical desciption |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 2.5./2.5.1. |  | PERU-01-12-170-07-001 |  |  | A | PER | E | 8 | U2 | TSP | 001 | 00 | VHHR |  | PER-E-8-U2-TSP-001-00-VHHR | Unit 2 technical description of process control | Unit 2 technical description of process control |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
nije spremno
djelomično spremno
|  |  | FŠ | spremno za slanje | [15 empty] | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO
|  |  | FŠ | samo en/samo mne verzija spremna za slanje | [15 empty] | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO
predano u ICS-u
postoji u DD, na čekanju do daljnjeg
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO

## GoW3
[5 empty] | ` | [17 empty] | Document Review Stage 1 |  |  |  |  | Document Review Stage 2 |  |  |  |  | Document Review Stage 3
|  |  |  | GOW 3 | [18 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Numbering acc to Tehnical specification | Number Duplication colored red | Design | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Document Title IN FOLDER | Document Title | Document title in folder (MNE) | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 3.2./3.2.3 | JM/RV | PERU-01-13-111-11-001 |  |  | A | PER | E | 2 | U3 | FLD | 001 | 00 | VHHR |  | PER-E-2-U3-FLD-001-00-VHHR | Unit 3 HyCon governor series 400 block diagram | HyCon governor series 400 block diagram |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 3.2./3.2.3 | FŠ | PERU-01-13-111-12-001 |  |  | A | PER | E | 2 | U3 | SCH | 001 | 00 | VHHR |  | PER-E-2-U3-SCH-001-00-VHHR | Unit 3 turbine governor topology | Turbine governor topology | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 3.2./3.2.2. | TT | PERU-01-13-111-14-003 |  |  | A | PER | E | 2 | U3 | ASB | 001 | 00 | VHHR |  | PER-E-2-U3-ASB-001-00-VHHR | Unit 3 turbine governor cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 3.2./3.2.2. |  | PERU-01-13-111-23-002 |  |  | A | PER | E | 2 | U3 | LST | 001 | 00 | VHHR |  | PER-E-2-U3-LST-001-00-VHHR | Unit 3 turbine governor equipment specification and quantities | Equipment specification and quantities - electrical part |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 3.2./3.2.2. | TT | PERU-01-13-111-31-001 |  |  | A | PER | E | 2 | U3 | SCH | 002 | 00 | VHHR |  | PER-E-2-U3-SCH-002-00-VHHR | Unit 3 turbine governor circuit diagram | Circuit diagrams |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 3.2./3.2.2. | TT | PERU-01-13-111-33-001 |  |  | A | PER | E | 2 | U3 | ROU | 001 | 00 | VHHR |  | PER-E-2-U3-ROU-001-00-VHHR | Unit 3 turbine governor cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 3.1. | AA | PERU-01-13-111-61-002 |  |  | A | PER | E | 2 | U3 | FAT | 001 | 00 | VHHR |  | PER-E-2-U3-FAT-001-00-VHHR | Unit 3 turbine governor cubicle FAT report | FAT-Factory Acceptance Test program - electrical part |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 3.1. | AA | PERU-01-13-111-52-001 |  |  | A | PER | E | 2 | U3 | CMM | 001 | 00 | VHHR |  | PER-E-2-U3-CMM-001-00-VHHR | Unit 3 turbine governor cubicle SAT report | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 3.1. |  | PERU-01-13-111-70-002 |  |  | A | PER | E | 2 | U3 | MAN | 002 | 00 | VHHR |  | PER-E-2-U3-MAN-002-00-VHHR |  | Operation and maintenance manual - electrical part |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
III | II | 3.1. |  | PERU-01-13-111-70-003 |  |  | A | PER | E | 2 | U3 | MAN | 001 | 00 | VHHR |  | PER-E-2-U3-MAN-001-00-VHHR |  | HMI operating manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti | spremno sve, pregledati
I | III | 3.2./3.2.3 |  | PERU-01-13-111-34-002 |  |  | A | PER | E | 2 | U3 | SOF | 100 | 00 | VHHR |  | PER-E-2-U3-SOF-100-00-VHHR | Unit 3 turbine governor signal list | Turbine governor signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list | spremno sve, pregledati
I | III | 3.2./3.2.3 | FŠ | PERU-01-13-111-34-003 |  |  | A | PER | E | 2 | U3 | SOF | 101 | 00 | VHHR |  | PER-E-2-U3-SOF-101-00-VHHR | Unit 3 transfer functions and modelling | Transfer functions and modelling | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO |  | EN spremno, MNE verzija ima "Projekat izvedenog stanja" umjesto "Projekat izvedenog objekta dvaput na naslovnoj, plus pečat izgleda zrnato, kao da je screenshot; ne mogu naći word
I | III | 3.5./3.5.2. | FŠ | PERU-01-13-170-31-001 |  |  | A | PER | E | 8 | U3 | SCH | 001 | 00 | VHHR |  | PER-E-8-U3-SCH-001-00-VHHR | Unit 3 process control circuit diagram | Circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 3.5./3.5.2. | TT | PERU-01-13-170-14-002 |  |  | A | PER | E | 8 | U3 | ASB | 001 | 00 | VHHR |  | PER-E-8-U3-ASB-001-00-VHHR | Unit 3 process control cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 3.5./3.5.2. | TT | PERU-01-13-170-23-001 |  |  | A | PER | E | 8 | U3 | LST | 001 | 00 | VHHR |  | PER-E-8-U3-LST-001-00-VHHR | Unit 3 process control equipment specification and quantities | Equipment specification and quantities |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 3.5./3.5.2. | TT | PERU-01-13-170-33-001 |  |  | A | PER | E | 8 | U3 | ROU | 001 | 00 | VHHR |  | PER-E-8-U3-ROU-001-00-VHHR | Unit 2 process control cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 3.4. | AA | PERU-01-13-170-61-001 |  |  | A | PER | E | 8 | U3 | FAT | 001 | 00 | VHHR |  | PER-E-8-U3-FAT-001-00-VHHR | Unit 3 process control cubicles FAT report | FAT-Factory Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
I | III | 3.5./3.5.3. | TT | PERU-01-13-170-34-001 |  |  | A | PER | E | 8 | U3 | SOF | 100 | 00 | VHHR |  | PER-E-8-U3-SOF-100-00-VHHR | Unit 3 turbine governor signal list | Unit process control signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 3.5./3.5.3. | TT | PERU-01-13-170-34-002 |  |  | A | PER | E | 8 | U3 | SCH | 002 | 00 | VHHR |  | PER-E-8-U3-SCH-002-00-VHHR | Unit 3 overview of logical connections | Overview of logical connections |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
II | II | 3.4. | AA | PERU-01-13-170-52-001 |  |  | A | PER | E | 8 | U3 | CMM | 001 | 00 | VHHR |  | PER-E-8-U3-CMM-001-00-VHHR | Unit 3 process control SAT report | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 3.3. |  | PERU-01-13-170-70 -001 |  |  | A | PER | E | 8 | U3 | MAN | 001 | 00 | VHHR |  | PER-E-8-U3-MAN-001-00-VHHR |  | Operation and maintenance manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 3.2./3.2.1. | JM | PERU-01-13-111-07-002 |  |  | A | PER | E | 2 | U3 | TSP | 001 | 00 | VHHR |  | PER-E-2-U3-TSP-001-00-VHHR | Unit 3 turbine governor technical desciption | Unit 3 turbine governor technical desciption |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 3.5./3.5.1. | JM | PERU-01-13-170-07-001 |  |  | A | PER | E | 8 | U3 | TSP | 001 | 00 | VHHR |  | PER-E-8-U3-TSP-001-00-VHHR | Unit 3 technical description of process control | Unit 3 technical description of process control |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
nije spremno
treba pregledati/ne znam stanje
|  |  | FŠ | spremno za slanje | [15 empty] | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO
|  |  | FŠ | samo en/samo mne verzija spremna za slanje | [15 empty] | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO
predano u ICS-u, ubaciti u folder
postoji u DD ali ne znam je li to zadnja verzija
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO

## GoW 4
|  |  |  | GOW 4 | [18 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Number Duplication colored red | D | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Supplier Document No. | Document Title IN FOLDER | Document Title | Document title in folder (MNE) | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 4.2./4.2.3 | JM/RV | PERU-01-14-111-11-001 |  | A | PER | E | 2 | U4 | FLD | 001 | 00 | VHHR |  | PER-E-2-U4-FLD-001-00-VHHR |  | Unit 4 HyCon governor series 400 block diagram | HyCon governor series 400 block diagram |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 4.2./4.2.3 | FŠ | PERU-01-14-111-12-001 |  | A | PER | E | 2 | U4 | SCH | 001 | 00 | VHHR |  | PER-E-2-U4-SCH-001-00-VHHR |  | Unit 4 turbine governor topology | Turbine governor topology | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 4.2./4.2.2. | TT | PERU-01-14-111-14-003 |  | A | PER | E | 2 | U4 | ASB | 001 | 00 | VHHR |  | PER-E-2-U4-ASB-001-00-VHHR |  | Unit 4 turbine governor cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 4.2./4.2.2. |  | PERU-01-14-111-23-002 |  | A | PER | E | 2 | U4 | LST | 001 | 00 | VHHR |  | PER-E-2-U4-LST-001-00-VHHR |  | Unit 4 turbine governor equipment specification and quantities | Equipment specification and quantities - electrical part |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 4.2./4.2.2. | TT | PERU-01-14-111-31-001 |  | A | PER | E | 2 | U4 | SCH | 002 | 00 | VHHR |  | PER-E-2-U4-SCH-002-00-VHHR |  | Unit 4 turbine governor circuit diagram | Circuit diagrams |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 4.2./4.2.2. | TT | PERU-01-14-111-33-001 |  | A | PER | E | 2 | U4 | ROU | 001 | 00 | VHHR |  | PER-E-2-U4-ROU-001-00-VHHR |  | Unit 4 turbine governor cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 4.1. | AA | PERU-01-14-111-61-002 |  | A | PER | E | 2 | U4 | FAT | 001 | 00 | VHHR |  | PER-E-2-U4-FAT-001-00-VHHR |  | Unit 4 turbine governor cubicle FAT report | FAT-Factory Acceptance Test program - electrical part |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 4.1. | AA | PERU-01-14-111-52-001 |  | A | PER | E | 2 | U4 | CMM | 001 | 00 | VHHR |  | PER-E-2-U4-CMM-001-00-VHHR |  | Unit 4 turbine governor cubicle SAT report | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 4.1. | AA | PERU-01-14-111-70-002 |  | A | PER | E | 2 | U4 | MAN | 002 | 00 | VHHR |  | PER-E-2-U4-MAN-002-00-VHHR |  |  | Operation and maintenance manual - electrical part |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
III | II | 4.1. |  | PERU-01-14-111-70-003 |  | A | PER | E | 2 | U4 | MAN | 001 | 00 | VHHR |  | PER-E-2-U4-MAN-001-00-VHHR |  |  | HMI operating manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti | spremno sve, pregledati
I | III | 4.2./4.2.3 |  | PERU-01-14-111-34-002 |  | A | PER | E | 2 | U4 | SOF | 100 | 00 | VHHR |  | PER-E-2-U4-SOF-100-00-VHHR |  | Unit 4 turbine governor signal list | Turbine governor signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list | spremno sve, pregledati
I | III | 4.2./4.2.3 | FŠ | PERU-01-14-111-34-003 |  | A | PER | E | 2 | U4 | SOF | 101 | 00 | VHHR |  | PER-E-2-U4-SOF-101-00-VHHR |  | Unit 4 transfer functions and modelling | Transfer functions and modelling | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO |  | EN spremno, MNE verzija ima "Projekat izvedenog stanja" umjesto "Projekat izvedenog objekta dvaput na naslovnoj, plus pečat izgleda zrnato, kao da je screenshot; ne mogu naći word
I | III | 4.5./4.5.2. | FŠ | PERU-01-14-170-31-001 |  | A | PER | E | 8 | U4 | SCH | 001 | 00 | VHHR |  | PER-E-8-U4-SCH-001-00-VHHR |  | Unit 4 process control circuit diagram | Circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 4.5./4.5.2. | TT | PERU-01-14-170-14-002 |  | A | PER | E | 8 | U4 | ASB | 001 | 00 | VHHR |  | PER-E-8-U4-ASB-001-00-VHHR |  | Unit 4 process control cubicle assembly drawings | Cubicle assembly drawings |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 4.5./4.5.2. | TT | PERU-01-14-170-23-001 |  | A | PER | E | 8 | U4 | LST | 001 | 00 | VHHR |  | PER-E-8-U4-LST-001-00-VHHR |  | Unit 4 process control equipment specification and quantities | Equipment specification and quantities |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 4.5./4.5.2. | TT | PERU-01-14-170-33-001 |  | A | PER | E | 8 | U4 | ROU | 001 | 00 | VHHR |  | PER-E-8-U4-ROU-001-00-VHHR |  | Unit 2 process control cable diagrams | Cable diagrams |  |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 4.4. | AA | PERU-01-14-170-61-001 |  | A | PER | E | 8 | U4 | FAT | 001 | 01 | VHHR |  | PER-E-8-U4-FAT-001-01-VHHR |  | Unit 4 process control cubicles FAT report | FAT-Factory Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
I | III | 4.5./4.5.3. | TT | PERU-01-14-170-34-001 |  | A | PER | E | 8 | U4 | SOF | 100 | 00 | VHHR |  | PER-E-8-U4-SOF-100-00-VHHR |  | Unit 4 process control signal list | Unit process control signal list |  |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 4.5./4.5.3. | TT | PERU-01-14-170-34-002 |  | A | PER | E | 8 | U4 | SCH | 002 | 00 | VHHR |  | PER-E-8-U4-SCH-002-00-VHHR |  | Unit 4 overview of logical connections | Overview of logical connections |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
II | II | 4.4. | AA | PERU-01-14-170-52-001 |  | A | PER | E | 8 | U4 | CMM | 001 | 01 | VHHR |  | PER-E-8-U4-CMM-001-01-VHHR |  | Unit 4 process control SAT report | SAT-Site Acceptance Test program |  |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 4.3. | TT | PERU-01-14-170-70 -001 |  | A | PER | E | 8 | U4 | MAN | 001 | 01 | VHHR |  | PER-E-8-U4-MAN-001-01-VHHR |  |  | Operation and maintenance manual |  |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-04-04; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 4.2./4.2.1. | JM | PERU-01-14-111-07-002 |  | A | PER | E | 2 | U4 | TSP | 001 | 00 | VHHR |  | PER-E-2-U4-TSP-001-00-VHHR |  | Unit 4 turbine governor technical desciption | Unit 4 turbine governor technical desciption |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 4.5./4.5.1. | JM | PERU-01-14-170-07-001 |  | A | PER | E | 8 | U4 | TSP | 001 | 00 | VHHR |  | PER-E-8-U4-TSP-001-00-VHHR |  | Unit 4 technical description of process control | Unit 4 technical description of process control |  |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
nije spremno
treba pregledati/ne znam stanje
|  |  | FŠ | spremno za slanje | [15 empty] | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO
|  |  | FŠ | samo en/samo mne verzija spremna za slanje | [15 empty] | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO
predano u ICS-u, ubaciti u folder
postoji u DD ali ne znam je li to zadnja verzija
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO
|  |  | FŠ | [16 empty] | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO

## GoW 6
[5 empty] | ` | [18 empty] | Document Review Stage 1 |  |  |  |  | Document Review Stage 2 |  |  |  |  | Document Review Stage 3
|  |  |  | GOW 7 | [19 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Numbering acc to Tehnical specification | Number Duplication colored red | D | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Supplier Document No. | Document title in folder | Document title in folder (MNE) | Document Title | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 6.2./6.2.3. |  | PERU-01-16-111-14-003 |  | PERU-01-16-111-14-003 - A | A | PER | E | 2 | U6 | ASB | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ASB-001-00-VHHR | 22044-DD-EE-02-06-104 | Unit 6 turbine governor cubicle assembly drawings |  | Cubicle assembly drawings |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.2./6.2.3. | FŠ | PERU-01-16-111-31-001 |  | PERU-01-16-111-31-001 - A | A | PER | E | 2 | U6 | SCH | 002 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-002-00-VHHR | 22044-DD-EE-02-06-100 | Unit 6 turbine governor circuit diagram | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO | Circuit diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
III | II | 6.2. |  | PERU-01-16-111-70-003 |  | PERU-01-16-111-70-003 - A | A | PER | E | 2 | U6 | MAN | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-MAN-001-00-VHHR | 22044-DD-EE-02-06-400 |  |  | HMI operating manual |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-03-06; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 6.2./6.2.4. |  | PERU-01-16-111-34-003 |  | PERU-01-16-111-34-003 - A | A | PER | E | 2 | U6 | SOF | 101 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SOF-101-00-VHHR | 22044-DD-EE-02-06-302 | Unit 6 transfer functions and modelling |  | Transfer functions and modelling |  | Izlazna dokumentacija -> As Built, fale editabilni fajlovi
I | III | 6.2./6.2.3. |  | PERU-01-16-111-23-002 |  | PERU-01-16-111-23-002 - A | A | PER | E | 2 | U6 | LST | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-LST-001-00-VHHR | 22044-DD-EE-02-06-102 | Unit 6 turbine governor equipment specification and quantities |  | Equipment specification and quantities - electrical part |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.2./6.2.3. |  | PERU-01-16-111-33-001 |  | PERU-01-16-111-33-001 - A | A | PER | E | 2 | U6 | ROU | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ROU-001-00-VHHR | 22044-DD-EE-02-06-101 | Unit 6 turbine governor cable diagrams |  | Cable diagrams |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 6.2. |  | PERU-01-16-111-61-002 |  | PERU-01-16-111-61-002 - A | A | PER | E | 2 | U6 | FAT | 001 | 01 | VHHR | Richter Thomas | PER-E-2-U6-FAT-001-01-VHHR | 22044-DD-EE-02-06-200 | Unit 6 turbine governor cubicle FAT report(_signed) |  | FAT-Factory Acceptance Test program - electrical part |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 6.2. |  | PERU-01-16-111-52-001 |  | PERU-01-16-111-52-001 - A | A | PER | E | 2 | U6 | CMM | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-CMM-001-00-VHHR | 22044-DD-EE-02-06-210 | Unit 6 turbine governor cubicle SAT report(_signed) |  | Unit 6 turbine governor cubicle SAT report |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 6.2. |  | PERU-01-16-111-70-002 |  | PERU-01-16-111-70-002 - A | A | PER | E | 2 | U6 | MAN | 002 | 00 | VHHR | Richter Thomas | PER-E-2-U6-MAN-002-00-VHHR | 22044-DD-EE-02-06-401 |  |  | Operation and maintenance manual - electrical part |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-19; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 6.2./6.2.3. |  | PERU-01-16-111-31-002 |  | PERU-01-16-111-31-002 - A | A | PER | E | 2 | U6 | SCH | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-003-00-VHHR | 22044-DD-EE-02-06-110 | Unit 6 turbine A junction box circuit diagram |  | Unit 6 turbine A junction box circuit diagram |  | spremno sve, pregledati
I | III | 6.2./6.2.3. |  | PERU-01-16-111-31-003 |  | PERU-01-16-111-31-003 - A | A | PER | E | 2 | U6 | SCH | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-004-00-VHHR | 22044-DD-EE-02-06-111 | Unit 6 turbine B junction box circuit diagram |  | Unit 6 turbine B junction box circuit diagram |  | spremno sve, pregledati
I | III | 6.2./6.2.3. | FŠ | PERU-01-16-111-31-004 |  | PERU-01-16-111-31-004 - A | A | PER | E | 2 | U6 | SCH | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-005-00-VHHR | 22044-DD-EE-02-06-112 | Unit 6 inlet A junction box circuit diagram | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO | Unit 6 inlet A junction box circuit diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.2./6.2.3. | FŠ | PERU-01-16-111-31-005 |  | PERU-01-16-111-31-005 - A | A | PER | E | 2 | U6 | SCH | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-006-00-VHHR | 22044-DD-EE-02-06-113 | Unit 6 inlet B junction box circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO | Unit 6 inlet B junction box circuit diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.2./6.2.3. |  | PERU-01-16-111-14-005 |  | PERU-01-16-111-14-005 - A | A | PER | E | 2 | U6 | ASB | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ASB-003-00-VHHR | 22044-DD-EE-02-06-120 | Unit 6 turbine A junction box assembly drawing |  | Unit 6 turbine A junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.2./6.2.3. |  | PERU-01-16-111-14-006 |  | PERU-01-16-111-14-006 - A | A | PER | E | 2 | U6 | ASB | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ASB-004-00-VHHR | 22044-DD-EE-02-06-121 | Unit 6 turbine B junction box assembly drawing |  | Unit 6 turbine B junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.2./6.2.3. |  | PERU-01-16-111-14-007 |  | PERU-01-16-111-14-007 - A | A | PER | E | 2 | U6 | ASB | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ASB-005-00-VHHR | Unit 2 process control cable diagrams | Unit 6 inlet A junction box assembly drawing |  | Unit 6 inlet A junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.2./6.2.3. |  | PERU-01-16-111-14-008 |  | PERU-01-16-111-14-008 - A | A | PER | E | 2 | U6 | ASB | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ASB-006-00-VHHR | 22044-DD-EE-02-06-123 | Unit 6 inlet B junction box assembly drawing |  | Unit 6 inlet B junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.2./6.2.3. |  | PERU-01-16-111-33-002 |  | PERU-01-16-111-33-002 - A | A | PER | E | 2 | U6 | ROU | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ROU-003-00-VHHR | 22044-DD-EE-02-06-130 | Unit 6 turbine A junction box cable diagram |  | Unit 6 turbine A junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.2./6.2.3. |  | PERU-01-16-111-33-003 |  | PERU-01-16-111-33-003 - A | A | PER | E | 2 | U6 | ROU | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ROU-004-00-VHHR | 22044-DD-EE-02-06-131 | Unit 6 turbine B junction box cable diagram |  | Unit 6 turbine B junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.2./6.2.3. |  | PERU-01-16-111-33-004 |  | PERU-01-16-111-33-004 - A | A | PER | E | 2 | U6 | ROU | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ROU-005-00-VHHR | 22044-DD-EE-02-06-132 | Unit 6 inlet A junction box cable diagram |  | Unit 6 inlet A junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.2./6.2.3. |  | PERU-01-16-111-33-005 |  | PERU-01-16-111-33-005 - A | A | PER | E | 2 | U6 | ROU | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U6-ROU-006-00-VHHR | 22044-DD-EE-02-06-133 | Unit 6 inlet B junction box cable diagram |  | Unit 6 inlet B junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.2./6.2.1. |  | PERU-01-16-111-07-002 |  | PERU-01-16-111-07-002 - A | A | PER | E | 2 | U6 | TSP | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-TSP-001-00-VHHR | 22044-BD-EE-02-06-001 | Unit 6 technical description of turbine governor cubicle |  | Technical description of turbine governor cubicle |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 6.2./6.2.4. |  | PERU-01-16-111-11-001 |  | PERU-01-16-111-11-001 - A | A | PER | E | 2 | U6 | FLD | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-FLD-001-00-VHHR | 22044-BD-EE-02-06-002 | Unit 6 HyCon governor series 400 block diagram |  | HyCon governor series 400 block diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 6.2./6.2.4. |  | PERU-01-16-111-12-001 |  | PERU-01-16-111-12-001 - A | A | PER | E | 2 | U6 | SCH | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SCH-001-00-VHHR | 22044-BD-EE-02-06-003 | Unit 6 turbine governor topology |  | Turbine governor topology |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 6.2./6.2.4. |  | PERU-01-16-111-41 -001 |  | PERU-01-16-111-41 -001 - A | A | PER | E | 2 | U6 | SOF | 100 | 00 | VHHR | Richter Thomas | PER-E-2-U6-SOF-100-00-VHHR | 22044-DD-EE-02-06-301 | Unit 6 turbine governor signal list |  | Unit 6 turbine governor signal list |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 6.5./6.5.2 |  | PERU-01-16-170-14-002 |  | PERU-01-16-170-14-002 - A | A | PER | E | 8 | U6 | ASB | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ASB-001-00-VHHR | 22044-DD-EE-08-06-105 | Unit 6 process control assembly drawing |  | Cubicle assembly drawings |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.5./6.5.2 |  | PERU-01-16-170-23-001 |  | PERU-01-16-170-23-001 - A | A | PER | E | 8 | U6 | LST | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-LST-001-00-VHHR | 22044-DD-EE-08-06-103 | Unit 6 process control equipment specification and quantities |  | Equipment specification and quantities |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.5./6.5.2 | FŠ | PERU-01-16-170-31-001 |  | PERU-01-16-170-31-001 - A | A | PER | E | 8 | U6 | SCH | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-003-00-VHHR | 22044-DD-EE-08-06-100 | Unit 6 process control circuit diagram | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO | Circuit diagrams |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.5./6.5.2 | FŠ | PERU-01-16-170-33-001 |  | PERU-01-16-170-33-001 - A | A | PER | E | 8 | U6 | ROU | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ROU-001-00-VHHR | 22044-DD-EE-08-06-102 | Unit 6 process control cable diagrams | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO | Cable diagrams |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 6.5. |  | PERU-01-16-170-61-001 |  | PERU-01-16-170-61-001 - A | A | PER | E | 8 | U6 | FAT | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-FAT-001-00-VHHR | 22044-DD-EE-08-06-200 | Unit 6 process control FAT report(_signed) |  | FAT-Factory Acceptance Test program |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 6.5. |  | PERU-01-16-170-52-001 |  | PERU-01-16-170-52-001 - A | A | PER | E | 8 | U6 | CMM | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-CMM-001-00-VHHR | 22044-DD-EE-08-06-210 | Unit 6 process control SAT report(_signed) |  | SAT-Site Acceptance Test program |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 6.5. |  | PERU-01-16-170-70-001 |  | PERU-01-16-170-70-001 - A | A | PER | E | 8 | U6 | MAN | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-MAN-001-00-VHHR | 22044-DD-EE-08-06-401 | Unit 6 process control O&M instructions |  | Operation and maintenance manual |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2025-03-06; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 6.5./6.5.3. |  | PERU-01-16-170-12-002 |  | PERU-01-16-170-12-002 - A | A | PER | E | 8 | U6 | SCH | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-002-00-VHHR | 22044-DD-EE-08-06-101 | Unit 6 overview of logical connections |  | Overview of logical connections |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 6.5./6.5.2 | FŠ | PERU-01-16-153-33-001 |  | PERU-01-16-153-33-001 - A | A | PER | E | 8 | U6 | SCH | 004 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-004-00-VHHR | 22044-DD-EE-08-06-105 | Unit 6 subdistribution cubicle circuit diagram | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO | Unit subdistribution cubicle circuit diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.5./6.5.2 | FŠ | PERU-01-16-196-31-001 |  | PERU-01-16-196-31-001 - A | A | PER | E | 8 | U6 | SCH | 005 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-005-00-VHHR | 22044-BD-EE-08-06-110 | Unit 6 transformer cooling system control cubicle circuit diagram | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO | Transformer cooling water system control cubicle circuit diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.5./6.5.2 | FŠ | PERU-01-16-132-31-001 |  | PERU-01-16-132-31-001 - A | A | PER | E | 8 | U6 | SCH | 006 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-006-00-VHHR | 22044-BD-EE-08-06-120 | Unit 6 busbar duct fan control cubicle circuit diagram | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO | Busbar duct fan control cubicle circuit daigram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, backup u Tehničkoj
I | III | 6.5./6.5.2 |  | PERU-01-16-196-14-001 |  | PERU-01-16-196-14-001 - A | A | PER | E | 8 | U6 | ASB | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ASB-002-00-VHHR | 22044-BD-EE-08-06-111 | Unit 6 transformer cooling system assembly drawing |  | Transformer cooling water system control cubicle assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.5./6.5.2 |  | PERU-01-16-132-14-001 |  | PERU-01-16-132-14-001 - A | A | PER | E | 8 | U6 | ASB | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ASB-003-00-VHHR | 22044-BD-EE-08-06-121 | Unit 6 busbar duct fan control cubicle assembly drawing |  | Busbar duct fan control cubicle assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
II | II | 6.1. |  | PERU-01-16-150-61-001 |  | PERU-01-16-150-61-001 - A | A | PER | E | 8 | U6 | FAT | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-FAT-002-00-VHHR | 22044-DD-EE-08-06-202 | Unit 6 subdistribution cubicle - FAT report_signed |  | Unit 6 subdistribution cubicle FAT report |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
I | III | 6.5./6.5.2 |  | PERU-01-16-196-33-001 |  | PERU-01-16-196-33-001 - A | A | PER | E | 8 | U6 | ROU | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ROU-003-00-VHHR | 22044-DD-EE-08-06-120 | Unit 6 transformer cooling water control system cable diagram_PIO |  | Unit 6 transformer cooling water control system cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.5./6.5.2 |  | PERU-01-16-132-33-001 |  | PERU-01-16-132-33-001 - A | A | PER | E | 8 | U6 | ROU | 004 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ROU-004-00-VHHR | 22044-DD-EE-08-06-121 | Unit 6 busbar duct fan control system cable diagram_PIO |  | Unit 6 busbar duct fan control system cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 6.5./6.5.2 |  | PERU-01-16-150-33-001 |  | PERU-01-16-150-33-001 - A | A | PER | E | 8 | U6 | ROU | 005 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-ROU-005-00-VHHR | 22044-DD-EE-08-06-141 | Unit 6 subdistribution cubicle cable diagram |  | Unit 6 subdistribution cubicle cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | I | 2.2./2.2.3. |  | PERU-01-16-170-17-001 |  | PERU-01-16-170-17-001 - A | A | PER | C | 8 | U6 | LAY | 001 | 03 | VHHR | Bechtel Karl | PER-C-8-U6-LAY-001-03-VHHR | 22044-DD-CE-08-06-001 | Unit 6 general arrangement drawing |  | General arrangement drawing |  | Izlazna dokumentacija -> As Built (građevinski dio), spremni pdf i editable
I | III | 6.5./6.5.1. |  | PERU-01-16-170-07-001 |  | PERU-01-16-170-07-001 - A | A | PER | E | 8 | U6 | TSP | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-TSP-001-00-VHHR | 22044-BD-EE-08-06-001 | Unit 6 technical description of process control |  | Technical description of unit control system |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 6.5./6.5.2 |  | PERU-01-16-150-17-001 |  | PERU-01-16-150-17-001 - A | A | PER | E | 8 | U6 | LAY | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-LAY-001-00-VHHR | 22044-BD-EE-08-06-002 | Unit 6 subdistribution cubicle layout drawing |  | Unit subdistribution cubicle layout drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 6.5./6.5.3. |  | PERU-01-16-170-41-001 |  | PERU-01-16-170-41-001 - A | A | PER | E | 8 | U6 | SOF | 100 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SOF-100-00-VHHR | 22044-DD-EE-02-06-301 | Unit 6 process control signal list |  | Unit 6 process control signal list |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 6.5./6.5.3. |  | PERU-01-16-170-12-001 |  |  | A | PER | E | 8 | U6 | SCH | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U6-SCH-001-00-VHHR |  |  |  | Control system topology |  | ima u ASB, ali zadnje u Tehnička dokumentacija -> Power plant general, ovo bi trebali poslati ažuriranu verziju sad nakon KA1 i KA2 izmjena? Ne znam jel treba dodavati pečat
nije spremno
djelomično spremno
spremno za slanje
samo en/samo mne verzija spremna za slanje
predano u ICS-u
postoji u DD, na čekanju do daljnjeg

## GoW 7
[5 empty] | ` | [18 empty] | Document Review Stage 1 |  |  |  |  | Document Review Stage 2 |  |  |  |  | Document Review Stage 3
|  |  |  | GOW 7 | [19 empty] | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment |  |  | Contractor's Document Transmittal |  | EPCG Comment
Part No | Book No | Volume No | As Built document No(CSD) | Employer Identification | Numbering acc to Tehnical specification | Number Duplication colored red | D | Project | Part | SEGMENT | Unit /Object | Document Type | Document Number | Revision Number | Originator | VOITH specialist in charge | Document No. (CSD) | Supplier Document No. | Document title in folder | Document title in folder (MNE) | Document Title | Scheduled Submission | Current status of document | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result | Letter N | Date | EPCG Lettter N | Date | EPCG Review Result
I | III | 7.2./7.2.3. |  | PERU-01-17-111-14-003 |  | PERU-01-17-111-14-003 - A | A | PER | E | 2 | U7 | ASB | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ASB-001-00-VHHR | 22044-DD-EE-02-07-104 | Unit 7 turbine governor cubicle assembly drawings |  | Cubicle assembly drawings |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.2./7.2.3. | FŠ | PERU-01-17-111-31-001 |  | PERU-01-17-111-31-001 - A | A | PER | E | 2 | U7 | SCH | 002 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-002-00-VHHR | 22044-DD-EE-02-07-100 | Unit 7 turbine governor circuit diagram | PER-E-2-U7-SCH-002-00-VHHR - Agregat 7 strujne sheme ormara turbinskog regulatora_PIO | Circuit diagram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
III | II | 7.2. |  | PERU-01-17-111-70-003 |  | PERU-01-17-111-70-003 - A | A | PER | E | 2 | U7 | MAN | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-MAN-001-00-VHHR | 22044-DD-EE-02-07-400 |  |  | HMI operating manual |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-19; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 7.2./7.2.4. |  | PERU-01-17-111-34-003 |  | PERU-01-17-111-34-003 - A | A | PER | E | 2 | U7 | SOF | 101 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SOF-101-00-VHHR | 22044-DD-EE-02-07-302 | Unit 7 transfer functions and modelling |  | Transfer functions and modelling |  | EN spremno, MNE verzija ima "Projekat izvedenog stanja" umjesto "Projekat izvedenog objekta dvaput na naslovnoj, plus pečat izgleda zrnato, kao da je screenshot; ne mogu naći word
I | III | 7.2./7.2.3. |  | PERU-01-17-111-23-002 |  | PERU-01-17-111-23-002 - A | A | PER | E | 2 | U7 | LST | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-LST-001-00-VHHR | 22044-DD-EE-02-07-102 | Unit 7 turbine governor equipment specification and quantities |  | Equipment specification and quantities - electrical part |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.2./7.2.3. |  | PERU-01-17-111-33-001 |  | PERU-01-17-111-33-001 - A | A | PER | E | 2 | U7 | ROU | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ROU-001-00-VHHR | 22044-DD-EE-02-07-101 | Unit 7 turbine governor cable diagrams |  | Cable diagrams |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
II | II | 7.2. |  | PERU-01-17-111-61-002 |  | PERU-01-17-111-61-002 - A | A | PER | E | 2 | U7 | FAT | 001 | 01 | VHHR | Richter Thomas | PER-E-2-U7-FAT-001-01-VHHR | 22044-DD-EE-02-07-200 | Unit 7 turbine governor cubicle FAT report(_signed) |  | FAT-Factory Acceptance Test program - electrical part |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 7.2. |  | PERU-01-17-111-52-001 |  | PERU-01-17-111-52-001 - A | A | PER | E | 2 | U7 | CMM | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-CMM-001-00-VHHR | 22044-DD-EE-02-07-210 | Unit 7 turbine governor cubicle SAT report(_signed) |  | Unit 7 turbine governor cubicle SAT report |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 7.2. |  | PERU-01-17-111-70-002 |  | PERU-01-17-111-70-002 - A | A | PER | E | 2 | U7 | MAN | 002 | 00 | VHHR | Richter Thomas | PER-E-2-U7-MAN-002-00-VHHR | 22044-DD-EE-02-07-401 |  |  | Operation and maintenance manual - electrical part |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-19; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 7.2./7.2.3. |  | PERU-01-17-111-31-002 |  | PERU-01-17-111-31-002 - A | A | PER | E | 2 | U7 | SCH | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-003-00-VHHR | 22044-DD-EE-02-07-110 | Unit 7 turbine A junction box circuit diagram |  | Unit 7 turbine A junction box circuit diagram |  | spremno sve, pregledati
I | III | 7.2./7.2.3. |  | PERU-01-17-111-31-003 |  | PERU-01-17-111-31-003 - A | A | PER | E | 2 | U7 | SCH | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-004-00-VHHR | 22044-DD-EE-02-07-111 | Unit 7 turbine B junction box circuit diagram |  | Unit 7 turbine B junction box circuit diagram |  | spremno sve, pregledati
I | III | 7.2./7.2.3. | FŠ | PERU-01-17-111-31-004 |  | PERU-01-17-111-31-004 - A | A | PER | E | 2 | U7 | SCH | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-005-00-VHHR | 22044-DD-EE-02-07-112 | Unit 7 inlet A junction box circuit diagram | PER-E-2-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača A_PIO | Unit 7 inlet A junction box circuit diagram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
I | III | 7.2./7.2.3. | FŠ | PERU-01-17-111-31-005 |  | PERU-01-17-111-31-005 - A | A | PER | E | 2 | U7 | SCH | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-006-00-VHHR | 22044-DD-EE-02-07-113 | Unit 7 inlet B junction box circuit diagram | PER-E-2-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme razvodne kutije kuglastog zatvarača B_PIO | Unit 7 inlet B junction box circuit diagram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
I | III | 7.2./7.2.3. |  | PERU-01-17-111-14-005 |  | PERU-01-17-111-14-005 - A | A | PER | E | 2 | U7 | ASB | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ASB-003-00-VHHR | 22044-DD-EE-02-07-120 | Unit 7 turbine A junction box assembly drawing |  | Unit 7 turbine A junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.2./7.2.3. |  | PERU-01-17-111-14-006 |  | PERU-01-17-111-14-006 - A | A | PER | E | 2 | U7 | ASB | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ASB-004-00-VHHR | 22044-DD-EE-02-07-121 | Unit 7 turbine B junction box assembly drawing |  | Unit 7 turbine B junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.2./7.2.3. |  | PERU-01-17-111-14-007 |  | PERU-01-17-111-14-007 - A | A | PER | E | 2 | U7 | ASB | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ASB-005-00-VHHR | Unit 2 process control cable diagrams | Unit 7 inlet A junction box assembly drawing |  | Unit 7 inlet A junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.2./7.2.3. |  | PERU-01-17-111-14-008 |  | PERU-01-17-111-14-008 - A | A | PER | E | 2 | U7 | ASB | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ASB-006-00-VHHR | 22044-DD-EE-02-07-123 | Unit 7 inlet B junction box assembly drawing |  | Unit 7 inlet B junction box assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.2./7.2.3. |  | PERU-01-17-111-33-002 |  | PERU-01-17-111-33-002 - A | A | PER | E | 2 | U7 | ROU | 003 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ROU-003-00-VHHR | 22044-DD-EE-02-07-130 | Unit 7 turbine A junction box cable diagram |  | Unit 7 turbine A junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.2./7.2.3. |  | PERU-01-17-111-33-003 |  | PERU-01-17-111-33-003 - A | A | PER | E | 2 | U7 | ROU | 004 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ROU-004-00-VHHR | 22044-DD-EE-02-07-131 | Unit 7 turbine B junction box cable diagram |  | Unit 7 turbine B junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.2./7.2.3. |  | PERU-01-17-111-33-004 |  | PERU-01-17-111-33-004 - A | A | PER | E | 2 | U7 | ROU | 005 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ROU-005-00-VHHR | 22044-DD-EE-02-07-132 | Unit 7 inlet A junction box cable diagram |  | Unit 7 inlet A junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.2./7.2.3. |  | PERU-01-17-111-33-005 |  | PERU-01-17-111-33-005 - A | A | PER | E | 2 | U7 | ROU | 006 | 00 | VHHR | Richter Thomas | PER-E-2-U7-ROU-006-00-VHHR | 22044-DD-EE-02-07-133 | Unit 7 inlet B junction box cable diagram |  | Unit 7 inlet B junction box cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.2./7.2.1. |  | PERU-01-17-111-07-002 |  | PERU-01-17-111-07-002 - A | A | PER | E | 2 | U7 | TSP | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-TSP-001-00-VHHR | 22044-BD-EE-02-07-001 | Unit 7 technical description of turbine governor cubicle |  | Technical description of turbine governor cubicle |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.2./7.2.4. |  | PERU-01-17-111-11-001 |  | PERU-01-17-111-11-001 - A | A | PER | E | 2 | U7 | FLD | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-FLD-001-00-VHHR | 22044-BD-EE-02-07-002 | Unit 7 HyCon governor series 400 block diagram |  | HyCon governor series 400 block diagram |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.2./7.2.4. |  | PERU-01-17-111-12-001 |  | PERU-01-17-111-12-001 - A | A | PER | E | 2 | U7 | SCH | 001 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SCH-001-00-VHHR | 22044-BD-EE-02-07-003 | Unit 7 turbine governor topology |  | Turbine governor topology |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.2./7.2.4. |  | PERU-01-17-111-41 -001 |  | PERU-01-17-111-41 -001 - A | A | PER | E | 2 | U7 | SOF | 100 | 00 | VHHR | Richter Thomas | PER-E-2-U7-SOF-100-00-VHHR | 22044-DD-EE-02-07-301 | Unit 7 turbine governor signal list |  | Unit 7 turbine governor signal list |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
I | III | 7.5./7.5.2 |  | PERU-01-17-170-14-002 |  | PERU-01-17-170-14-002 - A | A | PER | E | 8 | U7 | ASB | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ASB-001-00-VHHR | 22044-DD-EE-08-07-105 | Unit 7 process control assembly drawing |  | Cubicle assembly drawings |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.5./7.5.2 |  | PERU-01-17-170-23-001 |  | PERU-01-17-170-23-001 - A | A | PER | E | 8 | U7 | LST | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-LST-001-00-VHHR | 22044-DD-EE-08-07-103 | Unit 7 process control equipment specification and quantities |  | Equipment specification and quantities |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.5./7.5.2 | FŠ | PERU-01-17-170-31-001 |  | PERU-01-17-170-31-001 - A | A | PER | E | 8 | U7 | SCH | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SCH-003-00-VHHR | 22044-DD-EE-08-07-100 | Unit 7 process control circuit diagram | PER-E-8-U7-SCH-003-00-VHHR - Agregat 7 strujne sheme master stanice_PIO | Circuit diagrams |  | treba ažurirati prikaz kabela od mjerenja temperatura i prijevode po shemama, to Fran rješava
I | III | 7.5./7.5.2 | FŠ | PERU-01-17-170-33-001 |  | PERU-01-17-170-33-001 - A | A | PER | E | 8 | U7 | ROU | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ROU-001-00-VHHR | 22044-DD-EE-08-07-102 | Unit 7 process control cable diagrams | PER-E-8-U7-ROU-001-00-VHHR - Agregat 7 kabelska lista master stanice_PIO | Cable diagrams |  | popraviti assignanje žile 5 u W5101, assignanje i prikaz kabela U7CJA10-W7001(2,3,4,5) pa nanovo izgenerirati
II | II | 7.5. |  | PERU-01-17-170-61-001 |  | PERU-01-17-170-61-001 - A | A | PER | E | 8 | U7 | FAT | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-FAT-001-00-VHHR | 22044-DD-EE-08-07-200 | Unit 7 process control FAT report(_signed) |  | FAT-Factory Acceptance Test program |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
II | II | 7.5. |  | PERU-01-17-170-52-001 |  | PERU-01-17-170-52-001 - A | A | PER | E | 8 | U7 | CMM | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-CMM-001-00-VHHR | 22044-DD-EE-08-07-210 | Unit 7 process control SAT report(_signed) |  | SAT-Site Acceptance Test program |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
III | II | 7.5. |  | PERU-01-17-170-70-001 |  | PERU-01-17-170-70-001 - A | A | PER | E | 8 | U7 | MAN | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-MAN-001-00-VHHR | 22044-DD-EE-08-07-401 | Unit 7 process control O&M instructions |  | Operation and maintenance manual |  | Izlazna dokumentacija -> Detail design -> Electrical -> 2024-04-19; dogovor je da će se raditi detaljni manuali na kraju, zasad preskočiti
I | III | 7.5./7.5.3. |  | PERU-01-17-170-12-002 |  | PERU-01-17-170-12-002 - A | A | PER | E | 8 | U7 | SCH | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SCH-002-00-VHHR | 22044-DD-EE-08-07-101 | Unit 7 overview of logical connections |  | Overview of logical connections |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.5./7.5.2 | FŠ | PERU-01-17-153-33-001 |  | PERU-01-17-153-33-001 - A | A | PER | E | 8 | U7 | SCH | 004 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SCH-004-00-VHHR | 22044-DD-EE-08-07-105 | Unit 7 subdistribution cubicle circuit diagram | PER-E-8-U7-SCH-004-00-VHHR - Agregat 7 strujne sheme ormara podrazvoda_PIO | Unit subdistribution cubicle circuit diagram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
I | III | 7.5./7.5.2 | FŠ | PERU-01-17-196-31-001 |  | PERU-01-17-196-31-001 - A | A | PER | E | 8 | U7 | SCH | 005 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SCH-005-00-VHHR | 22044-BD-EE-08-07-110 | Unit 7 transformer cooling system control cubicle circuit diagram | PER-E-8-U7-SCH-005-00-VHHR - Agregat 7 strujne sheme rashladnog sistema transformatora_PIO | Transformer cooling water system control cubicle circuit diagram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
I | III | 7.5./7.5.2 | FŠ | PERU-01-17-132-31-001 |  | PERU-01-17-132-31-001 - A | A | PER | E | 8 | U7 | SCH | 006 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SCH-006-00-VHHR | 22044-BD-EE-08-07-120 | Unit 7 busbar duct fan control cubicle circuit diagram | PER-E-8-U7-SCH-006-00-VHHR - Agregat 7 strujne sheme ormara za upravljanje ventilatorom šinskog kanala_PIO | Busbar duct fan control cubicle circuit daigram |  | en verzija spremna; mne verziju ažurira Fran, nakon čega ćemo imati i editable
I | III | 7.5./7.5.2 |  | PERU-01-17-196-14-001 |  | PERU-01-17-196-14-001 - A | A | PER | E | 8 | U7 | ASB | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ASB-002-00-VHHR | 22044-BD-EE-08-07-111 | Unit 7 transformer cooling system assembly drawing |  | Transformer cooling water system control cubicle assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.5./7.5.2 |  | PERU-01-17-132-14-001 |  | PERU-01-17-132-14-001 - A | A | PER | E | 8 | U7 | ASB | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ASB-003-00-VHHR | 22044-BD-EE-08-07-121 | Unit 7 busbar duct fan control cubicle assembly drawing |  | Busbar duct fan control cubicle assembly drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
II | II | 7.1. |  | PERU-01-17-150-61-001 |  | PERU-01-17-150-61-001 - A | A | PER | E | 8 | U7 | FAT | 002 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-FAT-002-00-VHHR | 22044-DD-EE-08-07-202 | Unit 7 subdistribution cubicle FAT report(_signed) |  | Unit 7 subdistribution cubicle FAT report |  | VOITH ICS, ubačeno od tamo u Izlaznu -> As built
I | III | 7.5./7.5.2 |  | PERU-01-17-196-33-001 |  | PERU-01-17-196-33-001 - A | A | PER | E | 8 | U7 | ROU | 003 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ROU-003-00-VHHR | 22044-DD-EE-08-07-120 | Unit 7 transformer cooling water control system cable diagram_PIO |  | Unit 7 transformer cooling water control system cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.5./7.5.2 |  | PERU-01-17-132-33-001 |  | PERU-01-17-132-33-001 - A | A | PER | E | 8 | U7 | ROU | 004 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ROU-004-00-VHHR | 22044-DD-EE-08-07-121 | Unit 7 busbar duct fan control system cable diagram_PIO |  | Unit 7 busbar duct fan control system cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | III | 7.5./7.5.2 |  | PERU-01-17-150-33-001 |  | PERU-01-17-150-33-001 - A | A | PER | E | 8 | U7 | ROU | 005 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-ROU-005-00-VHHR | 22044-DD-EE-08-07-141 | Unit 7 subdistribution cubicle cable diagram |  | Unit 7 subdistribution cubicle cable diagram |  | Izlazna dokumentacija -> As Built, editable kroz eplan backup
I | I | 2.2./2.2.3. |  | PERU-01-17-170-17-001 |  | PERU-01-17-170-17-001 - A | A | PER | C | 8 | U7 | LAY | 001 | 03 | VHHR | Bechtel Karl | PER-C-8-U7-LAY-001-03-VHHR | 22044-DD-CE-08-07-001 | Unit 7 general arrangement drawing |  | General arrangement drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.5./7.5.1. |  | PERU-01-17-170-07-001 |  | PERU-01-17-170-07-001 - A | A | PER | E | 8 | U7 | TSP | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-TSP-001-00-VHHR | 22044-BD-EE-08-07-001 | Unit 7 technical description of process control |  | Technical description of unit control system |  | Izlazna dokumentacija -> As Built, spremni pdf i editable
I | III | 7.5./7.5.2 |  | PERU-01-17-150-17-001 |  | PERU-01-17-150-17-001 - A | A | PER | E | 8 | U7 | LAY | 001 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-LAY-001-00-VHHR | 22044-BD-EE-08-07-002 | Unit 7 subdistribution cubicle layout drawing |  | Unit subdistribution cubicle layout drawing |  | Izlazna dokumentacija -> As Built, spremni pdf i editable, editable i u Tehničkoj
I | III | 7.5./7.5.3. |  | PERU-01-17-170-41-001 |  | PERU-01-17-170-41-001 - A | A | PER | E | 8 | U7 | SOF | 100 | 00 | VHHR | Bechtel Karl | PER-E-8-U7-SOF-100-00-VHHR | 22044-DD-EE-02-07-301 | Unit 7 process control signal list |  | Unit 7 process control signal list |  | Izlazna dokumentacija -> As Built, editable u Programi -> Symbol list
nije spremno
treba pregledati/ne znam stanje
spremno za slanje
samo en/samo mne verzija spremna za slanje
predano u ICS-u, ubaciti u folder
postoji u DD ali ne znam je li to zadnja verzija

## Abbreviations
DESIGN |  | OBJECT | PART |  | SEGMENT |  | UNIT/OBJECT |  | DOC TYPE |  | DOC NO. | REV | Originator
B |  | PER | E |  | 6 |  | U5 |  | SLD |  | 001 | 01 | ELNS |  | B-PER-E-6-U5-SLD-001-01-ELNS
B | BASIC |  | C | Civil | 1 | turbines and Appurtenant Equipment | U1 | UNIT 1 | BOQ | Bill of Quantities |  |  | VHPO | Voith Hydro Austria |  | Ibetsberger Franz
D | DETAIL |  | E | Electrical | 2 | Turbine Governors | U2 | UNIT 2 | CAL | Calculation |  |  | ELNS | Elnos |  | Richter Thomas
A | AS BUILT |  | I | Control System | 3 | Turbine Inlet Valves | U3 | UNIT 3 | CAT | Catalogues |  |  | IEE | IEE Technology |  | Bechtel Karl
F | Field Service Doc |  | M | Mechanical | 4 | Unit Excitation and Electrical Braking Systems | U4 | UNIT 4 | CDR | Construction Drawings |  |  | EPH | Energoprojekt hidroinženjering |  | Koppensteiner Stefan
NA | non applicaable |  | O | Other | 5 | Generator Voltage Equipment | U5 | UNIT 5 | CIV | Civil Drawings |  |  | IMP | Institute Mihajlo Pupin Belgrade |  | Speckl Markus
AD | Additional document |  | X | without information | 6 | High-Voltage (110 kV) Equipment | U6 | UNIT 6 | CRT | Certificates |  |  | EPCG | Elektroprivreda Crne Gore |  | Kapfhammer Matthias
|  |  | A | Arhitecture | 7 | Unit Electrical Protection Systems | U7 | UNIT 7 | DDD | Detail Design Documents |  |  | LANS |  |  | Vata Isodoro
|  |  | H | HVAC | 8 | Unit Control Systems | PO | POVIJA | DIM | Dimension Drawings |  |  | VHHR |  |  | Gayer Markus
|  |  | HP | Hydrological meaurements and piezzometers | 9 | Unit and Step-up Transformer Monitoring Systems | MK | MARIN KRST | FLD | Function Logic Diagrams |  |  | MPLJ | Montavar projekt Ljubljana |  | Kiskanc Mehmet
[5 empty] | 10 | Integral Information System | SL | SLANO | FOU | Foundation Drawings | [5 empty] | Saša Stefanović
[5 empty] | 11 | Equipment within Krupac Bottom Outlet Valve Chamber | VR | VRTAC | HSD | Health & Safety Documents
[5 empty] | 12 | Equipment within Slano Bottom Outlet Valve Chamber | KR | KRUPAC | INF | General Information
[5 empty] | 13 | Equipment within Vrtac Spillway and Bottom Outlet Valve Chamber | CO | COMMON DOC. | INS | Installation Drawings
[5 empty] | 14 | Equipment within Marin Krst Inlet Structure Valve Chamber | KA1&KA2 | UNITS KA1&KA2 | LAY | Layout Drawings
[5 empty] | N/A | Not applicable | KA1 | UNIT KA1 | LAO | Loading Drawings
[5 empty] | 15 | Equipment within Povija Surge Tank Valve Chamber | KA2 | UNIT KA2 | LST | Lists
[5 empty] | 16 | Equipment for Hydrological–Hydraulic Measurements | AUXPS | AUXILIARY POWER SUPPLY | MAN | Manuals
[5 empty] | N/A | Not applicable |  |  | ORG | Organizational Documents
[9 empty] | OTH | Others
[9 empty] | PID | P & I Diagrams
[9 empty] | QAD | QA / Testing related Documents
[9 empty] | ROU | Routing Plans
[9 empty] | RPT | Reports
[9 empty] | SCH | Schematic Diagrams
[9 empty] | SLD | Single Line Diagrams
[9 empty] | SOF | Software related Documents
[9 empty] | STY | Studies
[9 empty] | TDS | Technical Data Sheets
[9 empty] | TSP | Technical Specifications / Descriptions
[9 empty] | TYP | Typicals
[9 empty] | XXX | Without information
ITP
[9 empty] | ASB | Assembly Drawing
[9 empty] | WSD | Workshop drawing
[9 empty] | FAT | FAT Program
[9 empty] | ERC | Erection Instruction
[9 empty] | CMM | Commissioning Program
[9 empty] | PRT | Protocol